## Sheet1
Stand-up questions | Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6 | Week #7 | Week #8
TEAM : SERVERLESS SEEKERS | 02/10/2025-02/24/2025 | 02/25/2025-03/10/2025 | 03/11/2025-03/24/2025 | 03/25/2025-04/07/2025 | 04/08/2025-04/14/2025 | 04/15/2025-04/21/2025 | 04/22/2025-04/28/2025 | 04/29/2025-05/11/2025
Pratik Kamanahalli Mallikarjuna
What tasks did I work on / complete? | Initialized Next.js app, added Tailwind CSS, built navigation layout | Built search API, input validation, JSON output | Completed booking API, added confirmation email functionality | Created restaurant listing frontend, added filters and pagination | Hooked up register/login pages to backend | Refactored pages for reusability and responsiveness | Prepared project for deployment (vercel config) | Final bug fixes and feature toggles
What am I planning to work on next? | Design login/register forms and route logic | Implement booking API, connect to DB | Integrate cancel booking API | Setup edit/delete action handlers | Add error messages and success feedback | Final frontend polish and clean-up | Test app end-to-end on staging | Present demo
What tasks are blocked waiting on another team member? | NA | NA | NA | Waiting for delete API test |  | NA | NA | N/A
Dhruv Khut
What tasks did I work on / complete? | Created basic auth middleware, token generation logic | Developed frontend search & booking screens (static → dynamic) | Connected UI to search + booking APIs, tested frontend | Secured route access based on user roles | Implemented session management logic | Added toast alerts and consistent navigation | Supported integration testing | Created login walkthrough and onboarding guide
What am I planning to work on next? | Set up protected routes and start role-based access | Connect UI to APIs | Improve UI styling, error handling | Add loader/error components to UX | Write tests for middleware protection | Polish loading states and error UI | Prepare presentation assets | Submit GitHub + documentation
What tasks are blocked waiting on another team member? | Waiting for UI pages from Dhruv | Waiting for Dhruv’s booking API to be ready | N/A | N/A | NA | NA | N/A | NA
Nitya Reddy Yerram
What tasks did I work on / complete? | Designed Prisma schema for Users, Roles, Reviews, and Restaurants | Populated mock data for restaurants | Finalized test datasets, wrote SQL triggers for review logic | Optimized queries using Prisma & indexes | Finalized data validations and constraints in schema | Added fallback values for missing foreign key data | Verified schema compliance and app boot | Provided DB schema ER diagram and docs
What am I planning to work on next? | Run migrations, test with Prisma Studio | Create stored procedures for booking logic | Connect DB hooks with backend endpoints | Help with seed data adjustments | Add automatic role assignment on signup | Run final seed + DB consistency check | Create final SQL export and notes | Review grading checklist
What tasks are blocked waiting on another team member? | NA | NA | NA | NA | NA |  | NA | N/A
Rahul Dhingra
What tasks did I work on / complete? | Designed admin dashboard wireframes, created layout mock | Built basic admin dashboard UI | Built user management tables in admin panel | Added restaurant table views for admin | Created admin stats summary cards | Implemented user search and filters | Final UI refinements and bug fixing | Recorded admin-side demo
What am I planning to work on next? | Build base admin UI and connect routing | Implement remove restaurant API | Add user delete and edit functions | Integrate filters and batch delete | Add Chart Integration | Add review management tab | Work on PPT | Finalize README and deployment note
What tasks are blocked waiting on another team member? | NA | Waiting for Dhruv’s delete endpoint | Waiting on API for user role validation | NA | Waiting on backend data for reviews count | Waiting for seed data to include test reviews | NA | NA